## Cover Page
Big Data Course
HandAI: Vietnamese Primary School Handwriting Recognition System
Work Breakdown Structure
For students
ⓒ2023 SAMSUNG. All rights reserved.
Samsung Electronics Corporate Citizenship Office holds the copyright of this document.
This document is a literary property protected by copyright law so reprint and reproduction without permission are prohibited.
To use this document other than the curriculum of Samsung Innovation Campus, you must receive written consent from copyright holder.
Samsung Innovation Campus

## WBS
Capstone Project Work Breakdown Structure (WBS)
Done
In-progress
Delayed
Today
Project Team Name |  | Nguyễn Văn Duy Mạnh – Trần Hoài Nam
Project Topic |  | HandAI: Vietnamese Primary School Handwriting Recognition System
Task |  |  | Start date | End date | Responsibility | Deliverable | Task Status | W1 |  |  |  |  | W2 |  |  |  |  | W3 |  |  |  |  | W4
[8 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20
[8 empty] | 2024-07-23 | 2024-07-24 | 2024-07-25 | 2024-07-26 | 2024-07-27 | 2024-07-28 | 2024-07-29 | 2024-07-30 | 2024-07-31 | 2024-08-01 | 2024-08-02 | 2024-08-03 | 2024-08-04 | 2024-08-05 | 2024-08-06 | 2024-08-07 | 2024-08-08 | 2024-08-09 | 2024-08-10 | 2024-08-11
1. Project Research |  |  | 2024-07-22 | 2024-07-31 |  | Architecture Spec | Done | bar: 2024-07-23 to 2024-07-29
| 1.1. MOET primary penmanship curriculum & handwriting standards analysis |  | 2024-07-22 | 2024-07-26 | All members | Research Report | Done | bar: 2024-07-23
| 1.2. Vietnamese orthography & tonal diacritics literature review |  | 2024-07-25 | 2024-07-29 | All members | State-of-the-Art Survey | Done | bar: 2024-07-24 to 2024-07-25
| 1.3. Technical architecture & service boundary definition |  | 2024-07-27 | 2024-07-31 | Trần Hoài Nam | Architecture Specification | Done | bar: 2024-07-26 to 2024-07-28
2. Dataset Preparation |  |  | 2024-08-01 | 2024-08-14 |  | Audited HandAI-v1.2 | Done | bar: 2024-07-29
| 2.1. HandAI-v1.2 corpus curation & ingestion (59,747 line crops) |  | 2024-08-01 | 2024-08-07 | Nguyễn Văn Duy Mạnh | Raw Ingestion Manifest | Done | bar: 2024-07-30 to 2024-08-04
| 2.2. Deduplication via pHash & cryptographic SHA-256 filtering |  | 2024-08-05 | 2024-08-09 | Nguyễn Văn Duy Mạnh | Deduplication Report (0.4% dup) | Done | bar: 2024-07-30 to 2024-08-01
| 2.3. Multi-grade demographic stratification (Grades 1–5) |  | 2024-08-08 | 2024-08-12 | Nguyễn Văn Duy Mạnh | Grade Distribution Manifest | Done | bar: 2024-08-02
| 2.4. Document-disjoint train/val/test partitioning (70/15/15, Seed=42) |  | 2024-08-11 | 2024-08-14 | Nguyễn Văn Duy Mạnh | Frozen Split Manifests | Done | bar: 2024-08-03 to 2024-08-04
3. Image Processing |  |  | 2024-08-15 | 2024-08-29 |  | OpenCV Pipeline | Done | bar: 2024-08-05 to 2024-08-07
| 3.1. Adaptive contrast enhancement (CLAHE) & grayscale conversion |  | 2024-08-15 | 2024-08-19 | Nguyễn Văn Duy Mạnh | Preprocessing Module | Done | bar: 2024-08-05 to 2024-08-07
| 3.2. Otsu binarization & deskew angle correction |  | 2024-08-18 | 2024-08-22 | Nguyễn Văn Duy Mạnh | Deskew Filter | Done | bar: 2024-08-08 to 2024-08-11
| 3.3. Horizontal Projection Profile (HPP) line segmentation |  | 2024-08-21 | 2024-08-26 | Nguyễn Văn Duy Mạnh | HPP Segmenter | Done | bar: 2024-08-08 to 2024-08-11
| 3.4. Satellite Diacritic Consolidation algorithm implementation |  | 2024-08-24 | 2024-08-29 | Nguyễn Văn Duy Mạnh | Diacritic Merge Module | Done
4. OCR Model Development |  |  | 2024-08-30 | 2024-09-16 |  | best_cer.pth | Done
| 4.1. 320-token vocabulary definition with Vietnamese diacritics & math |  | 2024-08-30 | 2024-09-02 | Nguyễn Văn Duy Mạnh | vocab.json | Done
| 4.2. PyTorch CRNN architecture (Conv2d + GroupNorm + BiLSTM) |  | 2024-09-01 | 2024-09-06 | Trần Hoài Nam | model.py | Done
| 4.3. GPU-accelerated supervised model training with CTC loss |  | 2024-09-05 | 2024-09-12 | All members | Training Logs | Done
| 4.4. Greedy CTC decoder & micro-batching inference engine |  | 2024-09-11 | 2024-09-16 | Trần Hoài Nam | predict.py (best_cer.pth) | Done
5. AI Correction Development |  |  | 2024-09-17 | 2024-09-29 |  | Arbitration Engine | Done
| 5.1. Groq Cloud API integration (Llama-3.3-70b-versatile) |  | 2024-09-17 | 2024-09-20 | Trần Hoài Nam | Groq Client | Done
| 5.2. Google Gemini API integration (Gemini-4B / Flash fallback) |  | 2024-09-19 | 2024-09-23 | Trần Hoài Nam | Gemini Client | Done
| 5.3. Multi-consensus arbitration logic & Levenshtein selection |  | 2024-09-22 | 2024-09-26 | Trần Hoài Nam | Arbitration Engine | Done
| 5.4. Error recovery validation (67% rescue rate verification) |  | 2024-09-25 | 2024-09-29 | All members | Ablation Benchmark | Done
6. Backend Integration |  |  | 2024-09-30 | 2024-10-12 |  | Spring Boot Gateway | Done
| 6.1. Spring Boot 3.3 REST gateway & multipart upload endpoints |  | 2024-09-30 | 2024-10-04 | Trần Hoài Nam | HandAiOcrController | Done
| 6.2. MinIO S3 object storage for page images & line crop slices |  | 2024-10-02 | 2024-10-06 | Trần Hoài Nam | S3 Storage Service | Done
| 6.3. Internal AI proxying with security headers & 10MB limit |  | 2024-10-05 | 2024-10-09 | Trần Hoài Nam | OcrMultilineService | Done
| 6.4. Zero-login guest demonstration mode implementation |  | 2024-10-08 | 2024-10-12 | Trần Hoài Nam | Guest API Endpoints | Done
7. Mobile Integration |  |  | 2024-10-13 | 2024-10-23 |  | Expo Mobile Client | Done
| 7.1. React Native / Expo 51 camera viewfinder with aspect ratio guide |  | 2024-10-13 | 2024-10-17 | Trần Hoài Nam | handai-camera.tsx | Done
| 7.2. Interactive bounding box review & manual coordinate adjustment |  | 2024-10-16 | 2024-10-20 | Trần Hoài Nam | handai-review.tsx | Done
| 7.3. Client HTTP service & multipart binary upload transport |  | 2024-10-19 | 2024-10-23 | Trần Hoài Nam | handAiGuestApi.ts | Done
8. Analytics Dashboard |  |  | 2024-10-24 | 2024-11-03 |  | Analytics Screens | Done
| 8.1. Real-time Trial Analytics screen (8-metric quality report) |  | 2024-10-24 | 2024-10-28 | Trần Hoài Nam | handai-trial-analytics.tsx | Done
| 8.2. Global Analytics research dashboard & multi-session trends |  | 2024-10-27 | 2024-10-31 | Trần Hoài Nam | handai-analytics.tsx | Done
| 8.3. Native report export engine (Markdown, JSON, CSV formats) |  | 2024-10-30 | 2024-11-03 | Trần Hoài Nam | Export Utilities | Done
9. Evaluation System |  |  | 2024-11-04 | 2024-11-14 |  | CER / WER Engine | Done
| 9.1. Dynamic programming Levenshtein distance for CER calculation |  | 2024-11-04 | 2024-11-07 | Nguyễn Văn Duy Mạnh | CER Algorithm | Done
| 9.2. Word-level token edit distance for Word Error Rate (WER) |  | 2024-11-06 | 2024-11-09 | Nguyễn Văn Duy Mạnh | WER Algorithm | Done
| 9.3. Unicode NFD tone error analysis & homologous glyph matrix |  | 2024-11-08 | 2024-11-12 | Nguyễn Văn Duy Mạnh | Error Taxonomy Engine | Done
| 9.4. Expected Calibration Error (ECE) & 5-bin reliability tracking |  | 2024-11-10 | 2024-11-14 | Nguyễn Văn Duy Mạnh | Calibration Matrix | Done
10. Testing |  |  | 2024-11-15 | 2024-11-22 |  | 168 Unit Tests Pass | Done
| 10.1. Automated frontend test suite (168 unit & integration tests) |  | 2024-11-15 | 2024-11-18 | All members | Jest Test Suite | Done
| 10.2. Backend integration tests & controller mock testing |  | 2024-11-17 | 2024-11-20 | Trần Hoài Nam | Gradle Test Suite | Done
| 10.3. TypeScript type checking & physical Android device QA |  | 2024-11-19 | 2024-11-22 | All members | QA Audit Report | Done
11. Documentation |  |  | 2024-11-23 | 2024-11-30 |  | 13-Doc Package | Done
| 11.1. Complete 13-document HandAI research technical package |  | 2024-11-23 | 2024-11-26 | All members | Technical Docs (13 files) | Done
| 11.2. Capstone Final Report preparation & academic formatting |  | 2024-11-25 | 2024-11-28 | All members | HAND_AI_FINAL_CAPSTONE_REPORT.docx | Done
| 11.3. Action Plan & Evaluation Sheet finalization |  | 2024-11-27 | 2024-11-30 | All members | Action Plan & Eval Sheet | Done
12. Defense Preparation |  |  | 2024-12-01 | 2024-12-08 |  | Defense Slide Deck | Done
| 12.1. Capstone defense slide deck preparation (14 slides) |  | 2024-12-01 | 2024-12-04 | All members | HAND_AI_FINAL_PRESENTATION.pptx | Done
| 12.2. Live system demonstration script & guest flow dry runs |  | 2024-12-03 | 2024-12-06 | All members | Live Demo Runbook | Done
| 12.3. Q&A defense rehearsal & final project sign-off |  | 2024-12-05 | 2024-12-08 | All members | Defense Readiness Package | Done